## TestCases
Project Name |  | BAZAAR
PREPARED BY |  | Fatima Fayyaz
DATE |  | 2025-05-01
Domain
Milestone 1
TEST CASE ID | TEST CASE SCENARIO | TEST CASE DESCRIPTION | PRECONDITION | TEST STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | Status | Re-Testing Attempts | Test status after attempt
TC_BZR_001 | Verify Homepage Loads Successfully. | Verify that homepage loads all elements to the screen. | User has internet access and a supported browser. | Open the browser. Navigate to https://www.bazaar-uae.com/. | None | Homepage loads completely with all elements (header, banner, featured products, footer) visible. | As Expected | Passed
TC_BZR_002 | Verify Search Functionality. | Verify that when user searches with a valid text, system displays all relevant matches. | User has internet access and a supported browser. | Open the browser. Navigate to https://www.bazaar-uae.com/. Tap to search bar and send valid search keys. | "Apple Earpods" | System should correctly list down all matches in dropdown listing. | As Expected | Passed
TC_BZR_003 |  | Verify that when user searches with an in-valid text, system displays "No Record Found" | User has internet access and a supported browser. | Open the browser. Navigate to https://www.bazaar-uae.com/. Tap to search bar and send in-valid text keys. | "xcvbbnj" | System should display "No Record Found" text on screen with 0 search items. | Not working as expected. | Failed
TC_BZR_004 | Verify Add to Cart Functionality. | Verify that when user adds an item to cart, system should adds it into cart. | User has internet access and a supported browser. Add item into cart to place order. | Open the browser. Search an item from Search Bar. Go to that Item. Tap to 'Add to Cart' button. | None | System should adds an item to cart successfully. | As Expected | Passed

## Bugs
Date | Feature/Role/State | Issue Overview | Issue Description | Issue Type | Bug Nature | Priority | Severity | Status | Screenshots/ Comments | QA Comments | Dev Comments | Comment Added By (Developer name)
2025-05-01 | Checkout Step 1: Billing Page | Mandatory Address Fields Not Marked with Asterisk (*) but Required on Submission including: Floor #, Landmark, Area, Apartment. | When filling out the address form during checkout, several fields—Floor #, Landmark, Area, and Apartment—are not visually marked as mandatory (i.e., with a red asterisk *). However, when the user clicks the "Next" button without entering values in those fields, the system throws validation messages requesting input. | Functional | Non-Critical | Medium | Low | To-Do | https://paste.pics/T89XN
2025-05-01 | Checkout Step 1: Billing Page | Input Validations on Billing Address form | Fields like Floor # and Apartment # accept alphabetic characters, even though they are expected to only accept numeric values. | Functional | Critical | Low | Low | To-Do | https://paste.pics/T89XN
2025-05-01 | Checkout Step 2: Your Order Page | Incorrect "You Saved Total" Calculation on Order Summary Page | The "You Saved Total" value shown on the order summary page is incorrect. For an item originally priced at 15 AED with a 33% discount, the discounted price becomes 10.05 AED, after rounding it off, it is 10 AED. Despite this, the system displays a savings of 15 AED, which is mathematically and logically incorrect. It should be "5 AED" | Functional | Critical | High | High | To-Do | https://paste.pics/T8A07
2025-05-01 | Redeem Coupon 10% Discount. | Incorrect Discount Calculation on Order Summary Page. | User will get 10% more discount on an already discounted amount which is 10 AED. So after applying 10% discount on 10 AED, it should be (10 * 0.10 = 9 AED). System is displaying wrong calculated amount i.e. 3 AED | Functional | Critical | High | High | To-Do | https://paste.pics/T8A1S
2025-05-01 | Search Bar on Homepage | Search bar functionality isn't working upon typing incorrect text. | System didn't display " No Record Found" after in-valid search on search bar text field. | Functional | Critical | High | Low | To-Do

## Test_Summary
IDE | VS Code
Testing Tool Used: | Cypress with Mocha Framework
Automated Features: | Site Visit
Test Case 01: | Register for Coupon
Providing Details "Name & Phone Number"
Reedemption of Coupon
Copied Coupon to Clipboard
Test Case 02: | Product Searching through Search Bar
Item Adding to Cart
Test Case 03: | Basic Validation Checks
Logo Visibility Check
Click on About Us Navigational Tab

## Sheet1
Test Case 01:
describe('Discounted Coupon Redemption', () => {
it('Register for Coupon', () => {
cy.visit('https://www.bazaar-uae.com/')
cy.wait(3000);
cy.get('#name').type('Fatima Fayyaz');
cy.wait(5000);
cy.get('#phone').type('0110120017');
cy.wait(5000);
cy.get('#submitRegister').click();
cy.get('#couponRectangle > button > span').click();
cy.get('#couponModal > div > div > div.product__modal-close.p-absolute.z_index > button').click();
})
});
--------------------
Test Case 02:
describe('Product Searching & Adding Item to Cart', () => {
it ('Searching and Item Addition', () => {
cy.visit('https://www.bazaar-uae.com/');
cy.wait(3000);
cy.contains('button', 'Click Here to shop online')
.should('be.visible')
.click({ force: true }); // Use force in case overlay blocks it
cy.get('.header__search-box > input').type('Apple EarPods with Lightning');
cy.get('#root > header > div > div.header__nav__container > div.header__info > div > div > div.col-xl-8.col-lg-9.my-4 > div > div.header__search.f-left.d-none.d-sm-block > form > div > div > ul > li > a').click();
// cy.get('.header__search-box > button').click();
cy.get('#root > header > div > div.header__nav__container > div.header__info > div > div > div.col-xl-8.col-lg-9.my-4 > div > div.header__search.f-left.d-none.d-sm-block > form > div > div > ul > li') // Replace with your dropdown button selector
.should('be.visible')
.click();
cy.scrollTo(0, 1000);
cy.get('.add-to-cart-btn').click();
cy.wait(1000);
cy.scrollTo(0, 200);
cy.get('#root > section.product__area.box-plr-75.pb-70 > div > div:nth-child(1) > div.col-xxl-7.col-xl-7.col-lg-7 > div > div > div.product__details-quantity.mb-20 > div > div.pro-cart-btn > button').click();
cy.wait(3000);
cy.scrollTo(0, 0);
cy.wait(2000);
//cy.get('#root > header > div > div.header__nav__container > div.header__info > div > div > div.col-xl-8.col-lg-9.my-4 > div > div.cart__mini-wrapper.d-none.d-md-flex.f-right.p-relative > div > ul > li:nth-child(4) > a.t-y-btn.t-y-btn-border.w-100.mb-10').click();
cy.get('#root > header > div > div.header__nav__container > div.header__info > div > div > div.col-xl-8.col-lg-9.my-4 > div > div.cart__mini-wrapper.d-none.d-md-flex.f-right.p-relative > a').click();
})
});
-------------------
Test Case 03:
describe(' Elements Visibility on product page', () => {
it('should display and show the logo on screen', () => {
// Visit the product detail page
cy.visit('https://www.bazaar-uae.com/product-details/');
// Verify if logo is visible
cy.get('.logo > a > img') .should('be.visible');
cy.wait(3000);
// Verify About Us Tab is clickable and navigational
cy.get('.main-menu > #mobile-menu > ul > :nth-child(2) > a').should('be.visible').click();
});
});

## Loom Video Link
Link: | https://www.loom.com/share/cb2f907ee3604ae7a388a40b1117f135